## Progress Planning and Tracking
Project Name: | 03-Management System for Non-Profits
Report Date: | 2025-08-31
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3 |  |  |  | C-Day
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23
Requirements & Solution Outline | Meet with stakeholder(s) | 0% | Current Status Memo | Ella, Fatih, Evan | 2025-08-24: 5
| Define requirements |  |  | Ella, Fatih, Evan | 2025-08-24: 5; 2025-08-31: 10
| Review requirements with stakeholder(s) | 0% |  | Ella, Fatih, Evan | 2025-09-07: 15
Stakeholder Mapping Document | Create stakeholder mapping document | 0% |  | Tyler | 2025-09-07: 10; 2025-09-14: 5
Implementation Plan | Define tech required * | 0% |  | Tyler | 2025-09-14: 10
| Research CRM and Project Management Software | 0% |  | Ella, Evan | 2025-09-14: 10; 2025-09-21: 10; 2025-09-28: 10
Cost Breakdown | Research upgrade options and costs | 0% |  | Fatih, Tyler | 2025-09-28: 5; 2025-10-05: 5
Solution and configuration rationale | Develop report for best Software Solution | 0% |  | Ella, Fatih | 2025-09-28: 10; 2025-10-05: 10
| Create prototype account for the Software Service selected | 0% |  | Tyler, Evan | 2025-09-28: 10; 2025-10-05: 15
Implementation Roadmap | Test prototype | 0% |  | Tyler, Evan | 2025-10-05: 5; 2025-10-12: 10
Proof of Concept | Develop working and complete Proof of Concept | 0% |  | Tyler, Evan | 2025-10-12: 5; 2025-10-19: 10; 2025-10-26: 10
| Review original requirements | 0% |  | Ella, Fatih | 2025-10-19: 10; 2025-10-26: 20; 2025-11-02: 20
| Test Product for Quality Assurance | 0% |  | Evan, Tyler | 2025-11-02: 20; 2025-11-09: 20
User Guide | Develop User Guide and Documentation | 0% |  | Ella, Fatih | 2025-11-02: 10; 2025-11-09: 20
Final report | Presentation preparation | 0% |  | Whole Group | 2025-11-16: 15; 2025-11-23: 10
| Poster preparation | 0% |  | Whole Group | 2025-11-23: 15
| Final report submission to D2L and project owner | 0% |  | Evan | 2025-11-23: 5
|  |  | Total work hours | 350 | 10 | 10 | 25 | 25 | 10 | 35 | 35 | 15 | 20 | 30 | 50 | 40 | 15 | 30
* formally define how you will develop this project including source code management
Legend
Planned | 350 Hours
Delayed
Number | Work: man hours